## tab_captions
tab.name | caption
surveyplantab | Dates, port calls and duration of the survey off South-West Africa.
reqparttab | Main types of expertise required and number of participants (scientific team only).
sciencethemestab | Science Plan themes for which this survey is most relevant and associated projects.
equipmenttab | Overview of component sampled, and equipment to be used during the survey. Overview of the gear codes to be used in the Cruise Logger system, detailed information about the rigging of the equipment as well as technical drawings and other specifications of the various equipment can be found in the Nansen wiki site.
datahandovertab | Data collected and overview of procedures for data hand-over to partners (all collected data will be stored at the IMR server).
collectedsamplestab | Samples to be collected, preservation and follow-up work.
biosamplingtab | Biological sampling envisioned for priority species as well as other species in the catch for Leg 4.1.
plannedparticipantstab | List of people planned to participate on the survey.
addsamplingtab | Data entry spreadsheet example.
taxonomytab | Invertebrate families for which biolocical samples are to be collected for taxonomic courses.
acousticcattab | Allocation of acoustic densities to species groups.
transectpostab | Survey Track positions for the June/July South African recruit survey.
transectranktab | Ranking of transects (order of priority within each stratum). Note: In the event of adverse weather or other unforeseen delays, the cruise leader/co-cruise leader is expected to remove transects as needed to ensure completion of the survey. It is important to assess the situation prior to the start of a stratum, and identify the need for removal of transects.
matstagetab | Gonad stage descriptions for anchovy, sardine and round herring used by the Department of Forestry, Fisheries and the Environment.
fatstageanchtab | Fat stage descriptions for anchovy used by the Department of Forestry, Fisheries and the Environment.
fatstagesarhtab | Fat stage descriptions for sardine and round herring used by the Department of Forestry, Fisheries and the Environment.

## fig_captions
fig.name | caption
surveyareamap | Leg 4.1 survey acoustic transects and strata in South-West Africa for small pelagic recruitment purposes.
scienceplan | Main pillars and research themes of the EAF-Nansen Programme.
catchsamplingworkflow | Overview of sampling procedures in the fish laboratory.
anchovyfat | Fat stage scale for anchovy to be used during Leg 4.1
sardinefat | Fat stage scale for sardine and round sardinella to be used during Leg 4.1
geneticsamplingprot | Labelled Eppendorf vials to be used for storing genetic samples

## surveyplantab
Survey Name | Duration in days | Departure | Arrival | Port of Departure | Port of Arrival
Leg 4.1 Small pelagic fish in South Africa (Orange River - Port Alfred) | 32 | 11/06/22 | 12/07/22 | Walvis Bay | Cape Town
A: Walvis Bay to Cape Town | 16 | 11/06/22 | 26/06/22 | Cape Town | Cape Town
B: Cape Town to Cape Town | 16 | 26/06/22 | 12/07/22 | Cape Town | Cape Town

## sciencethemestab
Theme | Project | Focal point
Theme 1 | Identification guide to ichthyoplankton in Southwest Africa | Edoardo Mostarda (FAO), Stamatina Isari (IMR)
Theme 2 | Addressing population structure of shared pelagic stocks (*T. capensis*) | Nikolaos Nikolioudakis (IMR)
Theme 3 | Community structure of mesopelagic fish | Bjørn Erik Axelsen (IMR)
Theme 9 | Oceanography, climate forcing and impacts on structure, diversity and productivity of marine ecosystems | Marek Ostrowski (IMR)

## reqparttab
Leg | Position/laboratory | Min personnel | DFN core team | DFN core team (IMR) | DFN core team (non-IMR) | Namibia | Angola | South Africa | FAO/External experts | Total non-IMR personnel | Missing personnel | Grand total
Leg4.1 | Cruise leader | 1 | 1 | 1
Leg4.1 | Co-cruise leader | 1 | 1 |  | 1 |  |  | 1 |  | 1
Leg4.1 | Water chemistry
Leg4.1 | Physical oceanography
Leg4.1 | Plankton biology
Leg4.1 | Fisheries biology / taxonomy | 11 | 2 | 2 |  | 1 | 2 | 6 |  | 9 | 0
Leg4.1 | Whale / Seabird observatory
Leg4.1 | Instrument personnel | 2 | 2 | 2
Leg4.1 | Other (acoustics) | 4 |  |  |  | 1 | 1 | 2 |  | 4 | 0 | 20

## plannedparticipantstab
LEG | PARTICIPANT | ROLE | E-MAIL | SEX | AFFILIATION | COUNTRY
Leg4.1_A+B | Bjørn-Erik Axelsen | Cruise leader | Bjoern.Erik.Axelsen@hi.no | M | IMR | NORWAY
Leg4.1_A+B | Diana Zarea-Perez | Fish Team Leader | diana.zaera-perez@hi.no | F | IMR | SPAIN
Leg4.1_A+B | Tom Wiliams | Fish Team Leader | tom.williams@hi.no | M | IMR | NORWAY
Leg4.1_A+B | Jan Frode Wilhelmsen | Chief Instruments Engineer | jan.frode.wilhelmsen@hi.no | M | IMR | NORWAY
Leg4.1_A+B | Jostein Solhaug | Instruments Engineer | jostein.solhaug@imr.no | M | IMR | NORWAY
Leg4.1_A+B | Yonela Geja | Fish team | YGeja@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_A+B | Johan Mhlongo | Fish team | ZwMhlongo@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_A+B | Winston April | Fish team | WApril@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_A+B | Ashok Bali | Fish team | ABali@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_A+B | Gino Jarvis | Fish team | GJarvis@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_A+B | Nomzolisi Mxunyelwa | Fish team | NMxunyelwa@dffe.gov.za | F | DFFE | SOUTH AFRICA
Leg4.1_A+B | Joana Vihemba de Sousa Pinheiro | Fish team | jovisopy2@gmail.com | F | INIP | ANGOLA
Leg4.1_A+B | Lennox Maliza | Other (Acoustics) | Lmaliza@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_A+B | Stela Maria Madeira Diogo Pedro | Other (Acoustics) | StelaPedro30@hotmail.com | F | INIP | ANGOLA
Leg4.1_A+B | Daniel Nortey | Fish team | dannylantei@gmail.com | M | FSSD | GHANA
Leg4.1_A+B | Priscilla Ankamah | Fish team | ankamah.P@yahoo.com | F | FSSD | GHANA
Leg4.1_A+B | Wendell Quartey-Papafio | Fish team | wenbeck5@yahoo.com | M | FSSD | GHANA
Leg4.1_A+B | Olivia Horvey | Fish team | ohorvey38@gmail.com | F | FSSD | GHANA
Leg4.1_A | Janet Coetzee | Co-Cruise leader | JCoetzee@dffe.gov.za | F | DFFE | SOUTH AFRICA
Leg4.1_A | Monique van Neel | Fish team | MoWilliams@dffe.gov.za | F | DFFE | SOUTH AFRICA
Leg4.1_A | Dumisani Ntiyantiya | Fish team | DNtiyantiya@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_A | Jean Mciwigi | Other (Acoustics) | JMwicigi@dffe.gov.za | F | DFFE | SOUTH AFRICA
Leg4.1_B | Fannie Shabangu | Co-Cruise leader | Fshabangu@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_B | Carl van der Lingen | Fish team | CVDLingen@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_B | Vumani Adonis | Fish team | VAdonis@dffe.gov.za | M | DFFE | SOUTH AFRICA
Leg4.1_B | Dumisani Ntiyantiya | Other (Acoustics) | DNtiyantiya@dffe.gov.za | M | DFFE | SOUTH AFRICA

## equipmenttab
SPD Code | English name | Norwegian name | Data or Samples | Responsible for logging
3587 | Åkra trawl without floats (small, 228) | Åkratrål u/blåser (små, 228) | Fish, invertebrates, marine debris | Bridge officer
3588 | Åkra trawl with floats (small, 228) | Åkratrål m/blåser (små, 228) | Fish, invertebrates, marine debris | Bridge officer
3596 | Multpelt 624 | Multpelt 624 | Fish, invertebrates, marine debris | Bridge officer
3597 | Multpelt 624 with inner lining | Multpelt 624 m/inner nett | Fish, invertebrates, marine debris | Bridge officer
3598 | Multpelt 624 with inner lining and DeepVision | Multpelt 624 m/inner nett/DeepVision | Fish, invertebrates, marine debris with images | Bridge officer
3599 | Multpelt 624 with DeepVision | Multpelt 624 m/DeepVision | Fish, invertebrates, marine debris with images | Bridge officer
3031 | Gisund Super with floats | Gisund Super m/blåser | Fish, invertebrates, marine debris | Bridge officer
3032 | Gisund Super without floats | Gisund Super u/blåser | Fish, invertebrates, marine debris | Bridge officer
3033 | Gisund Super without floats, with strapping | Gisund Super m/strappetau, u/blåser | Fish, invertebrates, marine debris | Bridge officer
3034 | Gisund Super without floats, with tickler chain and strapping | Gisund Super m/strappetau/kjettingmatte, u/blåser | Fish, invertebrates, marine debris | Bridge officer
3548 | Macroplankton trawl large without floats | Makropl.tr. S u/blåser | Fish, invertebrates, marine debris | Bridge officer
3549 | Macroplankton trawl large with floats | Makropl.tr. S u/blåser | Fish, invertebrates, marine debris | Bridge officer
3136 | Beam trawl | Bomtrål | Fish, invertebrates, marine debris | Bridge officer
2105 | Phytoplankton net | Algehåv | Plankton | Bridge officer
2121 | Juday-36 cm | Juday-36 cm | Plankton | Bridge officer
2133 | WP II-56 cm | WP II-56 cm | Plankton | Bridge officer
2152 | Multinet-MIDI | Multinet-MIDI | Plankton | Bridge officer
2154 | Multinet-MAMMOTH | Multinet-MAMMOTH | Plankton | Bridge officer
2314 | Bongo 60 cm | Bongo 60 cm | Plankton | Bridge officer
2375 | MANTA-net | MANTA-net | Plankton, microplastics | Bridge officer
2410 | Benthic sledge | Bunnslede | Benthos | Bridge officer
2502 | Box corer grab | Box corer grabb | Benthos, sediments | Bridge officer
7114 | CTD Seabird | CTD Seabird | Physical/Chemical oceanography | Bridge officer
Not required | Weather station |  | Meteorological data (wind speed, direction, temperature, light sensor) | Automatic
Not required | Thermosalinograph |  | Physical oceanography | Automatic
Not required | Acoustic Dopler Current Profiler |  | Physical oceanography | Automatic
missing!!! | CUFES (continuous underwater fish egg sampler) |  | Ichthyoplankton | ?????
Not required | Echo sounders (EK 80) |  | Fish, invertebrates acoustic data | Automatic
Not required | Omni-directional Fisheries sonar (SU90) |  | Fish acoustic data | Automatic
Not required | Olex (with input from EK80) |  | Bathymetry | Automatic
Not required |  |  | Mammals and seabirds | Observer

## datahandovertab
Data types | Data | after the survey | at the post survey meeting | upon request | not collected/stored | analyzed by partner country | analyzed through the Science Plan
Acoustic data | EK80 narrowband (CW) | x
Acoustic data | EK80 broadband (FM) |  |  |  | x
Acoustic data | MS70 |  |  |  | x
Acoustic data | ME70 |  |  |  | x
Acoustic data | SU90 | x
Acoustic data | SH90 |  |  |  | x
Acoustic data | SBP300 |  |  |  | x
Acoustic data | EM302 |  |  |  | x
Acoustic data | EM710 |  |  |  | x
Physics | CTD probe |  |  |  | x
Physics | CTD Underway |  |  | x
Physics | ADCP 75kHz |  |  | x
Physics | ADCP 150kHz |  |  | x
Physics | LADCP |  |  |  | x
Physics | Thermosalinograph |  |  | x
Physics | Nutrients |  |  |  | x
Physics | pH |  |  |  | x
Physics | Total alkalinity |  |  |  | x
Physics | pCO2 |  |  |  | x
Physics | Chlorophyll *a* |  |  |  | x
Biology | Trawl catch data | x
Biology | Zooplankton biomass |  |  |  | x
Biology | Phytoplankton |  |  |  | x
Pollution | Microplastics |  |  |  | x
Observation platforms | VAMS |  |  |  | x
Observation platforms | WBAT |  |  |  | x
Observation platforms | Deep Vision |  |  | x
Observation platforms | Activity diary (Survey Logger/Toktlogger) | x
Observation platforms | Nansis survey backup |  |  | x

## biosamplingtab
Species | Catch (Weight / Numbers) | Length frequency | Wet body weight | Sex & Maturity | Fat stage | Otoliths | Parasites | Morphometrics | Microplastics | Anthropogenic pollutants | Basic biology | Genetics
*Engraulis encrasicolus* | **YES** | **YES** | **YES** | **YES** | **YES** | **√** |  |  |  | **√**
*Etrumeus whiteheadi* | **YES** | **YES** | **YES** | **YES** | **YES** | **√** |  |  | **√** | **√**
*Lampanyctodes hectoris* | **YES** | **YES** | [8 empty] | **√**
*Maurolicus walvisensis* | **YES** | **YES** | [8 empty] | **√**
*Sardinops sagax* | **YES** | **YES** | **YES** | **YES** | **YES** | **√** | **√** |  |  | **√**
*Scomber japonicus* | **YES** | **YES** | [5 empty] | **√**
*Sufflogobius bibarbatus* | **YES** | **YES** | [8 empty] | **√**
*Trachurus capensis* | **YES** | **YES** | **YES** |  |  | **√** | **√** |  |  |  |  | **√**
Other mesopelagics | **YES** | **YES** | [8 empty] | **√**
Jellyfish | **YES** | **YES** | [9 empty] | **√**
All remaining species caught | **YES**
**YES:** | collected and recorded at sea
**√:** | samples retained for subsequent analysis

## collectedsamplestab
Gear/equipment | Analysis | Samples | Preservation | Amount of chemicals for preservation | Port of offloading | Type of transportation | Institution address | Contact details Leg 4.1(name, email, phone no) | Deadline for analysis | Data and sampling types for future usage and reference
CUFES samples | sardine and round herring eggs | Bottles (250 mL) | 5% formaldehyde solution | 10 Lt 37% formaldehyde solution | Cape Town | Road | DFFE^[Department of Forestry, Fisheries and the Environment] | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | otoliths from sardine, anchovy and round herring for age determination studies. | Vials | Dry |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | sardine (both juveniles and adults) for an analysis of infection by a “tetracotyle” type digenean parasite. | Whole fish | Frozen |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | round herring for monitoring of microplastic pollution in the SA marine pelagos. | Whole fish | Frozen (>20 cm length) |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | sardine, anchovy and round herring for assessment of their anthropogenic pollutant (herbicides, pharmaceuticals) levels. | Whole fish | Frozen |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | chub mackerel for collection of meristic information for stock/species identification. | Whole fish | Frozen |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | Hector’s lanternfish and lightfish for basic biology studies. | Whole fish | Frozen |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | uncommon and/or unidentified mesopelagic fish species for basic biology studies. | Whole fish | Frozen |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | pelagic gobies for basic biology studies. | Whole fish | Frozen |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | jellyfish (*Chrysaora* sp. and *Aequorea* sp.) tissue for genetic analysis | Jars | 96% ethanol for genetics |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | jellyfish (*Chrysaora* sp. and *Aequorea* sp.) | Whole organism if in good condition | 4% formaldehyde solution |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | horse mackerel for parasites analysis for stock identification. | Whole fish | Frozen |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | horse mackerel otoliths for stock identification. | vials | Dry |  | Cape Town | Road | DFFE | Carl van der Lingen, CVDLingen@dffe.gov.za
Trawl samples | horse mackerel fin clips for genetic analysis for stock identification. | fin-clips in vials | 96% ethanol for genetics |  | Bergen | Air | IMR | Nikolaos Nikolioudakis, nikolaos.nikolioudakis@hi.no
Trawl samples | unidentified taxa - Taxonomy | Whole individual | Frozen |  | To remain onboard |  | FAO | Peter Psomadakis, Peter.Psomadakis@fao.org

## matstagetab
Stage | State | Males | Females
I | Immature | Gonads very small, flat lappets close to fish’s anus, greyish or pink to transparent, depending on species. | Gonads very thin with a reddish colour.
II | Inactive/maturing | Gonads still small and flat but a little longer and whitish in colour. | Gonads still small and flat but a little longer and whitish in colour.
III | Active | Gonads opaque white | Minute ova visible; gonads >1/2 body length
IV | Active/ripening | Milkiness apparent at posterior end of gonad. | Gonads opaque yellow, vascular, ova discrete at posterior end.
V | Ripe | Gonads almost fill body cavity; opaque white; posterior half milky. | Gonads darker yellow, semi-transparent and almost fill body cavity; ova evenly dispersed throughout gonad.
VI | Ripe/running | Release milt when belly pressed. | Release eggs when belly pressed.
VII | Spent | Gonads elongated, flat, strap-like and bloodshot. | Gonads very bloodshot, sometimes gelatinous.

## additionalsamplingtab
SAMPLE FOR GENETICS
STA N° | SAMPLE N° | BOX N° | N°INSIDE | FAMILY | SPECIES/TAXA | TL (mm) | SL (mm) | DW | ML | PHOTO
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .

## fatstageanchtab
Stage | Description
I | No fat string associated with intestine or fat string barely visible
II | Fat string visible, thickness less than that of intestine
III | Fat string thickness approximately equal to intestine width
IV | Fat string thickness greater than intestine, but intestine partially visible
V | Intestine completely covered by fat string

## fatstagesarhtab
Stage | Description
I | Fat lines invisible or thin and indistinct
II | Depth greater than width of one or more fat lines
III | Pyloric fat line noticeably thicker than the other fat lines, and about one-third the thickness of the pyloric junction
IV | Depth greater than width for all fat lines but no fat lobes present
V | All fat lines slightly lobed, but no overlap between lobes
VI | Fat line lobes obvious and show some overlap
VII | Fat line lobes large, lots of overlap, and fundulus well-covered with fat

## acousticcattab
Acoustic category | Group | Taxon | Species
SARD | Sardinella | *Sardinella* spp. | *Sardinella maderensis*
*Sardinella aurita*
HMACK | Horse mackerel | *Trachurus* spp. | *Trachurus trecae*
*Trachurus capensis*
MACKE | Mackerel | *Scomber* sp. | *Scomber colias*
PILCH | Pilchard | *Sardinops* sp. | *Sardinops sagax*
ANCHO | Anchovy | *Engraulis encrasicolus* | *Engraulis encrasicolus*
RHERR | Round herring (redeye) | *Etrumeus whiteheadi* | *Etrumeus whiteheadi*
PEL1^[list of species is not exhaustive] | Pelagic group 1 | Clupeiformes^[Except *Sardinella* and *Engraulis* genera when explicit biomass estimates are provided for them] | *Ilisha africana*
*Engraulis encrasicolus*
*Etrumeus whiteheadi*
PEL2^[list of species is not exhaustive] | Pelagic group 2 | Carangidae^[Except *Trachurus* and *Scomber* genera when explicit biomass estimates are provided for them] | *Selene dorsalis*
*Chloroscombrus chrysurus*
*Decapterus rhonchus*
*Decapterus punctatus*
*Seriola carpenteri*
|  | Scombridae | *Auxis thazard*
*Sarda sarda*
*Scomber colias*
|  | Sphyraenidae | *Sphyraena guachancho*
|  | Trichiuridae | *Trichiurus lepturus*
*Lepidopus caudatus*
|  | *Brachydeuterus auritus* | *Brachydeuterus auritus*^[only rarely used as a separated acoustic category; therefore included in PEL2]
BOTT | Demersal species | Sparidae^[Main taxa group] | *Dentex angolensis*
*D. macrophthalmus*
*D. congoensis*
*D. canariensis*
*D. barnardi*
*Pagellus bellottii*
*Sparus caeruleostictus*
*S. pagrus africanus*
|  | Other taxa | *Saurida brasiliensis*
*Ariomma bondi*
*Pomadasys incisus*
*Galeoides decadactylus*
MESO1 | Lanternfish | *Lampanyctodes hectoris* | *Lampanyctodes hectoris*
MESO2 | Lightfish | *Maurolicus* spp. | *Maurolicus müllerii*
*Maurolicus walvisensis*
MESO^[if more acoustic categories are required the codes MESO3 and MESO4 should be used, and reflected in the table of the survey report] | Mesopelagic fish | (e.g. Myctophidae) | *Diaphus dumerili*
PLANK | Plankton | Plankton, Euphausiids
JELLY | Jellyfish | Jellyfish | Jellyfish
OTHER | Other | None of the above categories, or undetermined

## transectpostab
Latitude ° | Latitude Minutes | Longitude ° | Longitude Minutes | Latitude Decimalized ° | Longitude Decimalized ° | Location | Transect numbers
-28 | 38.445 | 16 | 26.61 | -28.641 | 16.443 | Inshore | Waypoint (Boundary line Orange River)
-28 | 44.04 | 16 | 33.368 | -28.734 | 16.556 | Inshore | Waypoint
-28 | 52.431 | 16 | 35.233 | -28.874 | 16.587 | Inshore | Transect 1
-29 | 2.454 | 16 | 15.19 | -29.041 | 16.253 | Offshore | Transect 1
-29 | 7.581 | 16 | 18.219 | -29.126 | 16.304 | Offshore | Transect 2
-28 | 56.16 | 16 | 40.36 | -28.936 | 16.673 | Inshore | Transect 2
-29 | 1.288 | 16 | 42.225 | -29.021 | 16.704 | Inshore | Waypoint
-29 | 6.183 | 16 | 48.051 | -29.103 | 16.801 | Inshore | Transect 3
-29 | 18.07 | 16 | 24.512 | -29.301 | 16.409 | Offshore | Transect 3
-29 | 22.732 | 16 | 26.843 | -29.379 | 16.447 | Offshore | Transect 4
-29 | 11.544 | 16 | 48.75 | -29.192 | 16.813 | Inshore | Transect 4
-29 | 15.04 | 16 | 49.449 | -29.251 | 16.824 | Inshore | Waypoint
-29 | 20.168 | 16 | 53.644 | -29.336 | 16.894 | Inshore | Transect 5
-29 | 31.356 | 16 | 31.271 | -29.523 | 16.521 | Offshore | Transect 5
-29 | 38.582 | 16 | 34.301 | -29.643 | 16.572 | Offshore | Transect 6
-29 | 26.928 | 16 | 57.84 | -29.449 | 16.964 | Inshore | Transect 6
-29 | 32.755 | 16 | 59.238 | -29.546 | 16.987 | Inshore | Waypoint
-29 | 35.319 | 16 | 59.238 | -29.589 | 16.987 | Inshore | Waypoint
-29 | 35.785 | 17 | 1.802 | -29.596 | 17.03 | Inshore | Transect 7
-29 | 47.439 | 16 | 37.796 | -29.791 | 16.63 | Offshore | Transect 7
-29 | 51.169 | 16 | 40.127 | -29.853 | 16.669 | Offshore | Transect 8
-29 | 40.214 | 17 | 1.335 | -29.67 | 17.022 | Inshore | Transect 8
-29 | 46.74 | 17 | 3.2 | -29.779 | 17.053 | Inshore | Waypoint
-29 | 54.665 | 17 | 6.23 | -29.911 | 17.104 | Inshore | Transect 9
-30 | 6.786 | 16 | 42.691 | -30.113 | 16.712 | Offshore | Transect 9
-30 | 16.575 | 16 | 47.352 | -30.276 | 16.789 | Offshore | Transect 10
-30 | 5.154 | 17 | 9.959 | -30.086 | 17.166 | Inshore | Transect 10
-30 | 8.184 | 17 | 10.658 | -30.136 | 17.178 | Inshore | Waypoint
-30 | 14.012 | 17 | 13.688 | -30.234 | 17.228 | Inshore | Waypoint (Boundary line Hondeklip Bay)
-30 | 20.072 | 17 | 15.552 | -30.335 | 17.259 | Inshore | Waypoint
-30 | 24.734 | 17 | 17.883 | -30.412 | 17.298 | Inshore | Transect 11
-30 | 37.787 | 16 | 52.479 | -30.63 | 16.875 | Offshore | Transect 11
-30 | 41.516 | 16 | 54.111 | -30.692 | 16.902 | Offshore | Transect 12
-30 | 27.997 | 17 | 19.98 | -30.467 | 17.333 | Inshore | Transect 12
-30 | 36.621 | 17 | 26.04 | -30.61 | 17.434 | Inshore | Transect 13
-30 | 49.441 | 17 | 0.636 | -30.824 | 17.011 | Offshore | Transect 13
-30 | 57.832 | 17 | 5.531 | -30.964 | 17.092 | Offshore | Transect 14
-30 | 45.245 | 17 | 30.934 | -30.754 | 17.516 | Inshore | Transect 14
-30 | 50.839 | 17 | 33.265 | -30.847 | 17.554 | Inshore | Waypoint
-30 | 57.599 | 17 | 37.693 | -30.96 | 17.628 | Inshore | Waypoint
-31 | 1.561 | 17 | 41.189 | -31.026 | 17.686 | Inshore | Transect 15
-31 | 14.614 | 17 | 15.552 | -31.244 | 17.259 | Offshore | Transect 15
-31 | 26.968 | 17 | 21.845 | -31.449 | 17.364 | Offshore | Transect 16
-31 | 13.449 | 17 | 48.414 | -31.224 | 17.807 | Inshore | Transect 16
-31 | 16.945 | 17 | 52.142 | -31.282 | 17.869 | Inshore | Waypoint
-31 | 19.742 | 17 | 52.609 | -31.329 | 17.877 | Inshore | Waypoint
-31 | 22.306 | 17 | 54.007 | -31.372 | 17.9 | Inshore | Transect 17
-31 | 39.322 | 17 | 19.747 | -31.655 | 17.329 | Offshore | Transect 17
-31 | 47.014 | 17 | 23.709 | -31.784 | 17.395 | Offshore | Transect 18
-31 | 28.833 | 17 | 59.6 | -31.481 | 17.993 | Inshore | Transect 18
-31 | 33.961 | 18 | 5.893 | -31.566 | 18.098 | Inshore | Waypoint
-31 | 36.525 | 18 | 6.592 | -31.609 | 18.11 | Inshore | Transect 19
-31 | 54.706 | 17 | 30.235 | -31.912 | 17.504 | Offshore | Transect 19
-32 | 0.766 | 17 | 34.197 | -32.013 | 17.57 | Offshore | Transect 20
-31 | 42.119 | 18 | 10.088 | -31.702 | 18.168 | Inshore | Transect 20
-31 | 48.878 | 18 | 13.351 | -31.815 | 18.223 | Inshore | Waypoint (Boundary line Doring Bay)
-31 | 52.142 | 18 | 14.982 | -31.869 | 18.25 | Inshore | Transect 21
-32 | 9.856 | 17 | 40.956 | -32.164 | 17.683 | Offshore | Transect 21
-32 | 13.819 | 17 | 43.519 | -32.23 | 17.725 | Offshore | Transect 22
-31 | 57.969 | 18 | 15.915 | -31.966 | 18.265 | Inshore | Transect 22
-32 | 2.397 | 18 | 17.779 | -32.04 | 18.296 | Inshore | Transect 23
-32 | 25.24 | 17 | 32.799 | -32.421 | 17.547 | Offshore | Transect 23
-32 | 28.969 | 17 | 33.265 | -32.483 | 17.554 | Offshore | Transect 24
-32 | 6.593 | 18 | 17.546 | -32.11 | 18.292 | Inshore | Transect 24
-32 | 13.586 | 18 | 18.711 | -32.226 | 18.312 | Inshore | Transect 25
-32 | 38.06 | 17 | 30.002 | -32.634 | 17.5 | Offshore | Transect 25
-32 | 42.022 | 17 | 31.4 | -32.7 | 17.523 | Offshore | Transect 26
-32 | 17.315 | 18 | 20.11 | -32.289 | 18.335 | Inshore | Transect 26
-32 | 20.112 | 18 | 18.012 | -32.335 | 18.3 | Inshore | Waypoint
-32 | 28.503 | 18 | 19.644 | -32.475 | 18.327 | Inshore | Transect 27
-32 | 55.075 | 17 | 27.438 | -32.918 | 17.457 | Offshore | Transect 27
-33 | 4.166 | 17 | 32.099 | -33.069 | 17.535 | Offshore | Transect 28
-32 | 54.842 | 17 | 50.744 | -32.914 | 17.846 | Inshore | Transect 28
-33 | 0.436 | 17 | 51.676 | -33.007 | 17.861 | Inshore | Waypoint
-33 | 4.632 | 17 | 55.405 | -33.077 | 17.923 | Inshore | Transect 29
-33 | 15.354 | 17 | 34.197 | -33.256 | 17.57 | Offshore | Transect 29
-33 | 23.046 | 17 | 38.625 | -33.384 | 17.644 | Offshore | Transect 30
-33 | 11.625 | 18 | 2.397 | -33.194 | 18.04 | Inshore | Transect 30
-33 | 19.55 | 18 | 7.757 | -33.326 | 18.129 | Inshore | Transect 31
-33 | 31.903 | 17 | 43.519 | -33.532 | 17.725 | Offshore | Transect 31
-33 | 37.497 | 17 | 46.782 | -33.625 | 17.78 | Offshore | Transect 32
-33 | 25.144 | 18 | 12.885 | -33.419 | 18.215 | Inshore | Transect 32
-33 | 30.505 | 18 | 18.478 | -33.508 | 18.308 | Inshore | Waypoint
-33 | 34.234 | 18 | 17.546 | -33.571 | 18.292 | Inshore | Waypoint
-33 | 39.362 | 18 | 23.839 | -33.656 | 18.397 | Inshore | Transect 33
-33 | 52.415 | 17 | 56.571 | -33.874 | 17.943 | Offshore | Transect 33
-33 | 55.911 | 17 | 58.435 | -33.932 | 17.974 | Offshore | Transect 34
-33 | 42.858 | 18 | 25.237 | -33.714 | 18.421 | Inshore | Transect 34
-33 | 46.355 | 18 | 25.47 | -33.773 | 18.425 | Inshore | Waypoint
-33 | 50.783 | 18 | 28.034 | -33.846 | 18.467 | Inshore | Transect 35
-34 | 6.866 | 17 | 56.105 | -34.114 | 17.935 | Offshore | Transect 35
-34 | 12.694 | 17 | 57.27 | -34.212 | 17.954 | Offshore | Transect 36
-34 | 2.205 | 18 | 18.711 | -34.037 | 18.312 | Inshore | Transect 36
-34 | 6.4 | 18 | 19.877 | -34.107 | 18.331 | Inshore | Transect 37
-34 | 15.258 | 18 | 0.999 | -34.254 | 18.017 | Offshore | Transect 37
-34 | 23.882 | 18 | 4.262 | -34.398 | 18.071 | Offshore | Transect 38
-34 | 15.724 | 18 | 21.741 | -34.262 | 18.362 | Inshore | Transect 38
-34 | 19.686 | 18 | 23.606 | -34.328 | 18.393 | Inshore | Waypoint
-34 | 23.183 | 18 | 27.801 | -34.386 | 18.463 | Inshore | Waypoint (Boundary line Cape Point)
-34 | 21.784 | 18 | 30.131 | -34.363 | 18.502 | Inshore | Waypoint
-34 | 8.731 | 18 | 28.267 | -34.146 | 18.471 | Inshore | Waypoint
-34 | 6.167 | 18 | 32.462 | -34.103 | 18.541 | Inshore | Waypoint
-34 | 6.167 | 18 | 38.288 | -34.103 | 18.638 | Inshore | Transect 39
-34 | 34.138 | 18 | 27.101 | -34.569 | 18.452 | Offshore | Transect 39
-34 | 38.333 | 18 | 33.394 | -34.639 | 18.557 | Offshore | Transect 40
-34 | 5.934 | 18 | 45.513 | -34.099 | 18.759 | Inshore | Transect 40
-34 | 7.1 | 18 | 48.31 | -34.118 | 18.805 | Inshore | Waypoint
-34 | 9.197 | 18 | 49.941 | -34.153 | 18.832 | Inshore | Waypoint
-34 | 11.295 | 18 | 48.31 | -34.188 | 18.805 | Inshore | Waypoint
-34 | 18.987 | 18 | 48.077 | -34.316 | 18.801 | Inshore | Transect 41
-34 | 42.063 | 18 | 39.687 | -34.701 | 18.661 | Offshore | Transect 41
-34 | 45.093 | 18 | 46.912 | -34.752 | 18.782 | Offshore | Transect 42
-34 | 22.716 | 18 | 55.535 | -34.379 | 18.926 | Inshore | Transect 42
-34 | 23.183 | 18 | 58.331 | -34.386 | 18.972 | Inshore | Waypoint
-34 | 22.017 | 19 | 0.895 | -34.367 | 19.015 | Inshore | Waypoint
-34 | 22.017 | 19 | 3.459 | -34.367 | 19.058 | Inshore | Waypoint
-34 | 24.115 | 19 | 5.789 | -34.402 | 19.096 | Inshore | Waypoint
-34 | 26.912 | 19 | 7.887 | -34.449 | 19.131 | Inshore | Waypoint
-34 | 26.912 | 19 | 9.984 | -34.449 | 19.166 | Inshore | Transect 43
-34 | 49.522 | 19 | 1.594 | -34.825 | 19.027 | Offshore | Transect 43
-34 | 51.619 | 19 | 6.489 | -34.86 | 19.108 | Offshore | Transect 44
-34 | 26.912 | 19 | 15.811 | -34.449 | 19.264 | Inshore | Transect 44
-34 | 27.611 | 19 | 18.375 | -34.46 | 19.306 | Inshore | Waypoint
-34 | 29.942 | 19 | 20.938 | -34.499 | 19.349 | Inshore | Waypoint
-34 | 32.04 | 19 | 21.404 | -34.534 | 19.357 | Inshore | Waypoint
-34 | 36.702 | 19 | 16.51 | -34.612 | 19.275 | Inshore | Waypoint
-34 | 39.732 | 19 | 17.442 | -34.662 | 19.291 | Inshore | Waypoint
-34 | 37.867 | 19 | 24.9 | -34.631 | 19.415 | Inshore | Waypoint
-34 | 39.033 | 19 | 26.066 | -34.651 | 19.434 | Inshore | Transect 45
-34 | 58.146 | 19 | 18.841 | -34.969 | 19.314 | Offshore | Transect 45
-35 | 1.176 | 19 | 25.366 | -35.02 | 19.423 | Offshore | Transect 46
-34 | 42.296 | 19 | 32.358 | -34.705 | 19.539 | Inshore | Transect 46
-34 | 44.86 | 19 | 33.523 | -34.748 | 19.559 | Inshore | Waypoint
-34 | 47.424 | 19 | 37.486 | -34.79 | 19.625 | Inshore | Transect 47
-35 | 5.605 | 19 | 30.261 | -35.093 | 19.504 | Offshore | Transect 47
-35 | 7.469 | 19 | 33.757 | -35.124 | 19.563 | Offshore | Transect 48
-34 | 48.589 | 19 | 40.748 | -34.81 | 19.679 | Inshore | Transect 48
-34 | 47.424 | 19 | 42.613 | -34.79 | 19.71 | Inshore | Waypoint
-34 | 47.657 | 19 | 48.206 | -34.794 | 19.803 | Inshore | Transect 49
-35 | 9.8 | 19 | 39.583 | -35.163 | 19.66 | Offshore | Transect 49
-35 | 14.695 | 19 | 51.469 | -35.245 | 19.858 | Offshore | Transect 50
-34 | 49.055 | 19 | 54.033 | -34.818 | 19.901 | Inshore | Transect 50
-34 | 51.386 | 20 | 1.258 | -34.856 | 20.021 | Inshore | Waypoint (Boundary line Cape Agulhas)
-34 | 48.589 | 20 | 5.22 | -34.81 | 20.087 | Inshore | Waypoint
-34 | 44.627 | 20 | 7.317 | -34.744 | 20.122 | Inshore | Transect 51
-35 | 14.229 | 20 | 14.076 | -35.237 | 20.235 | Offshore | Transect 51
-35 | 12.131 | 20 | 21.068 | -35.202 | 20.351 | Offshore | Transect 52
-34 | 42.762 | 20 | 14.076 | -34.713 | 20.235 | Inshore | Transect 52
-34 | 39.499 | 20 | 17.106 | -34.658 | 20.285 | Inshore | Transect 53
-35 | 13.763 | 20 | 25.263 | -35.229 | 20.421 | Offshore | Transect 53
-35 | 7.469 | 20 | 35.517 | -35.124 | 20.592 | Offshore | Transect 54
-34 | 31.807 | 20 | 26.894 | -34.53 | 20.448 | Inshore | Transect 54
-34 | 29.709 | 20 | 30.623 | -34.495 | 20.51 | Inshore | Waypoint
-34 | 28.777 | 20 | 34.585 | -34.48 | 20.576 | Inshore | Waypoint
-34 | 28.544 | 20 | 37.149 | -34.476 | 20.619 | Offshore | Transect 55
-35 | 3.507 | 20 | 45.306 | -35.058 | 20.755 | Offshore | Transect 55
-35 | 3.041 | 20 | 49.268 | -35.051 | 20.821 | Inshore | Transect 56
-34 | 29.01 | 20 | 40.878 | -34.483 | 20.681 | Inshore | Transect 56
-34 | 28.777 | 20 | 44.84 | -34.48 | 20.747 | Inshore | Waypoint
-34 | 29.709 | 20 | 48.802 | -34.495 | 20.813 | Inshore | Waypoint
-34 | 29.243 | 20 | 52.531 | -34.487 | 20.876 | Inshore | Waypoint (Boundary line Cape Infanta)
-34 | 25.98 | 20 | 53.463 | -34.433 | 20.891 | Inshore | Waypoint
-34 | 23.882 | 20 | 52.531 | -34.398 | 20.876 | Inshore | Waypoint
-34 | 22.949 | 20 | 57.192 | -34.382 | 20.953 | Inshore | Waypoint
-34 | 23.882 | 21 | 0.455 | -34.398 | 21.008 | Inshore | Transect 57
-34 | 59.078 | 21 | 8.845 | -34.985 | 21.147 | Offshore | Transect 57
-34 | 59.311 | 21 | 16.769 | -34.989 | 21.279 | Offshore | Transect 58
-34 | 24.581 | 21 | 8.146 | -34.41 | 21.136 | Inshore | Transect 58
-34 | 27.611 | 21 | 18.633 | -34.46 | 21.311 | Inshore | Waypoint
-34 | 25.747 | 21 | 24.46 | -34.429 | 21.408 | Inshore | Transect 59
-35 | 4.905 | 21 | 33.549 | -35.082 | 21.559 | Offshore | Transect 59
-35 | 3.973 | 21 | 52.194 | -35.066 | 21.87 | Offshore | Transect 60
-34 | 24.814 | 21 | 42.872 | -34.414 | 21.715 | Inshore | Transect 60
-34 | 22.017 | 21 | 53.825 | -34.367 | 21.897 | Inshore | Transect 61
-35 | 39.169 | 22 | 12.004 | -35.653 | 22.2 | Offshore | Transect 61
-35 | 28.913 | 22 | 21.793 | -35.482 | 22.363 | Offshore | Transect 62
-34 | 14.092 | 22 | 4.08 | -34.235 | 22.068 | Inshore | Transect 62
-34 | 13.859 | 22 | 8.042 | -34.231 | 22.134 | Inshore | Waypoint
-34 | 12.694 | 22 | 9.907 | -34.212 | 22.165 | Inshore | Waypoint (Boundary line Mossel Bay)
-34 | 8.032 | 22 | 9.44 | -34.134 | 22.157 | Inshore | Waypoint
-34 | 5.235 | 22 | 13.403 | -34.087 | 22.223 | Inshore | Waypoint
-34 | 4.302 | 22 | 19.695 | -34.072 | 22.328 | Inshore | Transect 63
-35 | 12.364 | 22 | 35.776 | -35.206 | 22.596 | Offshore | Transect 63
-35 | 5.371 | 22 | 43.467 | -35.09 | 22.724 | Offshore | Transect 64
-34 | 4.536 | 22 | 29.018 | -34.076 | 22.484 | Inshore | Transect 64
-34 | 0.806 | 22 | 34.378 | -34.013 | 22.573 | Inshore | Waypoint
-34 | 1.039 | 22 | 37.874 | -34.017 | 22.631 | Inshore | Waypoint
-34 | 2.438 | 22 | 40.437 | -34.041 | 22.674 | Inshore | Transect 65
-35 | 0.943 | 22 | 53.955 | -35.016 | 22.899 | Offshore | Transect 65
-34 | 55.349 | 23 | 10.269 | -34.922 | 23.171 | Offshore | Transect 66
-34 | 6.4 | 22 | 59.315 | -34.107 | 22.989 | Inshore | Transect 66
-34 | 6.4 | 23 | 13.299 | -34.107 | 23.222 | Inshore | Transect 67
-34 | 52.785 | 23 | 24.486 | -34.88 | 23.408 | Offshore | Transect 67
-34 | 53.251 | 23 | 30.778 | -34.888 | 23.513 | Offshore | Transect 68
-34 | 7.566 | 23 | 19.591 | -34.126 | 23.327 | Inshore | Transect 68
-34 | 8.032 | 23 | 25.884 | -34.134 | 23.431 | Inshore | Waypoint
-34 | 5.701 | 23 | 25.884 | -34.095 | 23.431 | Inshore | Waypoint
-34 | 3.603 | 23 | 23.554 | -34.06 | 23.393 | Inshore | Waypoint
-34 | 1.972 | 23 | 26.816 | -34.033 | 23.447 | Inshore | Waypoint
-34 | 1.505 | 23 | 31.944 | -34.025 | 23.532 | Inshore | Waypoint
-34 | 1.039 | 23 | 35.673 | -34.017 | 23.595 | Inshore | Transect 69
-34 | 48.356 | 23 | 46.626 | -34.806 | 23.777 | Offshore | Transect 69
-34 | 46.724 | 24 | 3.407 | -34.779 | 24.057 | Offshore | Transect 70
-34 | 3.137 | 23 | 53.152 | -34.052 | 23.886 | Inshore | Transect 70
-34 | 2.205 | 23 | 55.716 | -34.037 | 23.929 | Inshore | Waypoint
-34 | 4.769 | 24 | 2.008 | -34.079 | 24.033 | Inshore | Waypoint
-34 | 5.468 | 24 | 13.195 | -34.091 | 24.22 | Inshore | Transect 71
-34 | 45.093 | 24 | 22.751 | -34.752 | 24.379 | Offshore | Transect 71
-34 | 39.499 | 24 | 33.471 | -34.658 | 24.558 | Offshore | Transect 72
-34 | 9.43 | 24 | 26.48 | -34.157 | 24.441 | Inshore | Transect 72
-34 | 11.528 | 24 | 30.908 | -34.192 | 24.515 | Inshore | Waypoint
-34 | 12.694 | 24 | 36.967 | -34.212 | 24.616 | Inshore | Waypoint
-34 | 12.461 | 24 | 42.561 | -34.208 | 24.709 | Inshore | Waypoint
-34 | 14.558 | 24 | 50.019 | -34.243 | 24.834 | Inshore | Waypoint
-34 | 13.16 | 24 | 53.048 | -34.219 | 24.884 | Inshore | Waypoint (Boundary line Port Elizabeth)
-34 | 11.295 | 24 | 54.214 | -34.188 | 24.904 | Inshore | Waypoint
-34 | 9.197 | 24 | 52.582 | -34.153 | 24.876 | Inshore | Waypoint
-34 | 1.738 | 24 | 57.244 | -34.029 | 24.954 | Inshore | Transect 73
-34 | 36.469 | 25 | 5.401 | -34.608 | 25.09 | Offshore | Transect 73
-34 | 33.438 | 25 | 14.956 | -34.557 | 25.249 | Offshore | Transect 74
-33 | 58.941 | 25 | 6.799 | -33.982 | 25.113 | Inshore | Transect 74
-33 | 59.641 | 25 | 12.392 | -33.994 | 25.207 | Inshore | Waypoint
-34 | 2.205 | 25 | 19.85 | -34.037 | 25.331 | Inshore | Waypoint
-34 | 3.836 | 25 | 26.376 | -34.064 | 25.44 | Inshore | Waypoint
-34 | 2.904 | 25 | 31.503 | -34.048 | 25.525 | Inshore | Transect 75
-34 | 26.679 | 25 | 36.398 | -34.445 | 25.607 | Offshore | Transect 75
-34 | 23.416 | 25 | 52.479 | -34.39 | 25.875 | Offshore | Transect 76
-33 | 47.986 | 25 | 43.855 | -33.8 | 25.731 | Inshore | Transect 76
-33 | 44.49 | 25 | 50.614 | -33.741 | 25.844 | Inshore | Waypoint
-33 | 43.558 | 26 | 0.636 | -33.726 | 26.011 | Inshore | Transect 77
-34 | 20.852 | 26 | 9.725 | -34.348 | 26.162 | Offshore | Transect 77
-34 | 15.491 | 26 | 22.077 | -34.258 | 26.368 | Offshore | Transect 78
-33 | 45.888 | 26 | 15.319 | -33.765 | 26.255 | Inshore | Transect 78
-33 | 47.054 | 26 | 20.213 | -33.784 | 26.337 | Inshore | Waypoint
-33 | 46.355 | 26 | 26.039 | -33.773 | 26.434 | Inshore | Transect 79
-34 | 11.295 | 26 | 31.866 | -34.188 | 26.531 | Offshore | Transect 79
-34 | 5.002 | 26 | 48.413 | -34.083 | 26.807 | Offshore | Transect 80
-33 | 41.227 | 26 | 42.354 | -33.687 | 26.706 | Inshore | Transect 80
-33 | 37.73 | 26 | 54.473 | -33.629 | 26.908 | Inshore | Waypoint (Boundary line Port Alfred)

## transectranktab
Stratum | Transect # | Ranking | Stratum | Transect # | Ranking | Stratum | Transect # | Ranking | Stratum | Transect # | Ranking
A | 1 | 7 | D | 28 | 9 | F | 51 | 4 | I | 73 | 1
| 2 | 5 |  | 29 | 1 |  | 52 | 6 |  | 74 | 2
| 3 | 1 |  | 30 | 11 |  | 53 | 5 |  | 75 | 8
| 4 | 3 |  | 31 | 5 |  | 54 | 1 |  | 76 | 4
| 5 | 6 |  | 32 | 2 |  | 55 | 2 |  | 77 | 5
| 6 | 10 |  | 33 | 4 |  | 56 | 3 |  | 78 | 3
| 7 | 2 |  | 34 | 3 | G | 57 | 5 |  | 79 | 6
| 8 | 4 |  | 35 | 10 |  | 58 | 6 |  | 80 | 7
| 9 | 8 |  | 36 | 8 |  | 59 | 1
| 10 | 9 |  | 37 | 7 |  | 60 | 4
B | 11 | 4 |  | 38 | 6 |  | 61 | 3
| 12 | 9 | E | 39 | 4 |  | 62 | 2
| 13 | 3 |  | 40 | 8 | H | 63 | 5
| 14 | 5 |  | 41 | 12 |  | 64 | 9
| 15 | 1 |  | 42 | 10 |  | 65 | 4
| 16 | 6 |  | 43 | 7 |  | 66 | 2
| 17 | 7 |  | 44 | 9 |  | 67 | 7
| 18 | 8 |  | 45 | 6 |  | 68 | 1
| 19 | 10 |  | 46 | 5 |  | 69 | 6
| 20 | 2 |  | 47 | 11 |  | 70 | 8
C | 21 | 4 |  | 48 | 3 |  | 71 | 3
| 22 | 6 |  | 49 | 2 |  | 72 | 10
| 23 | 2 |  | 50 | 1
| 24 | 5
| 25 | 1
| 26 | 7
| 27 | 3

## taxonomytab
Family | Class
Squillidae - Mantis shrims | Crustacea
Aristeidae - Aristeid shrimps | Crustacea
Penaeidae - Penaeid shrimps | Crustacea
Palaemonidae - Palaemonid shrimps | Crustacea
Pandalidae - Pandalid shrimps | Crustacea
Nephropidae - True lobsters & langoustines | Crustacea
Palinuridae - Spiny lobsters | Crustacea
Scyllaridae - Slipper lobsters | Crustacea
Galatheidae Squat lobsters | Crustacea
Homolidae Paromolas | Crustacea
Calappidae - Box crabs | Crustacea
Majidae -Spider crabs | Crustacea
Geryonidae Deepsea crabs | Crustacea
Portunidae - Swimming crabs | Crustacea
Sepiidae - Cuttlefishes | Cephalopoda
Sepiolidae - Bobtail squids | Cephalopoda
Loliginidae - Inshore squids | Cephalopoda
Ommastephidae - Flying squids | Cephalopoda
Octopodidae - Benthic octopods | Cephalopoda