## SO.tab.captions
tab.name | caption
SOcruiseplantab | Dates, port calls and duration of the survey off North-West Africa.
SOreqparttab | Main types of expertise required and number of participants (scientific team only).
SOsciencethemestab | Science Plan themes for which this survey is most relevant and associated projects.
SOequipmenttab | Overview of component sampled and equipment used during the survey. Overview of the gear codes to be used in the Cruise Logger system, detailed information about the rigging of the equipment as well as technical drawings and other specifications of the various equipment can be found in the Nansen wiki site
SOdatahandovertab | Data collected and overview of procedures for data hand-over to partners (all collected data will be stored at the IMR server).
SOcollectedsamplestab | Samples to be collected, preservation and follow-up work.
SOplanktonsamplingtab | Plankton sampling locations for WP2, Bongo, Manta and phytoplankton sampling.
SOmatstagetab | Biological scales used for maturity stage.
SObiosamplingtab | Biological sampling envisioned for priority species as well as other species in the catch for Leg 2.
SOplannedparticipantstab | List of people planned to participate on the survey
SOtaxonomytab | Families for which biolocical samples are to be collected for taxonomic courses
SOaddsamplingtab | Data entry spreadsheet example

## SO.fig.captions
fig.name | caption
surveyareamapSOfig | Leg 2.1 (left) and Leg 2.2 (right) RV Dr Fridtjof Nansen Northwest Africa, 2022.
scienceplanSOfig | Main pillars and research themes of the EAF-Nansen Programme.
envtransectsSOfig | Sampling along environmental transects
epibenthosSOfig | Example of photograph with epibenthos to be taken at each demersal trawl station.
catchsamplingworkflowSOfig | Overview of sampling procedures in the fish laboratory.
bonyfishSOfig | Right figure caption is required
cartilagSOfig | Right figure caption is required
taggingbonyfishSOfig | Right figure caption is required
taggingbonyfishsmallSOfig | Right figure caption is required
barrelsSOfig | Right figure caption is required
boxesSOfig | Right figure caption is required
examplephotoSOfig | Right figure caption is required
cryoboxSOfig | Right figure caption is required
taggunfastenersSOfig | Right figure caption is required

## SO.sciencethemestab
Theme | Project | Focal point
Theme 1 | Identification guide to ichthyoplankton in Northwest Africa | Edoardo Mostarda (FAO), Stamatina Isari (IMR)
Theme 1 | Occurrence of egg and larvae (with emphasis on *Merluccius* spp. and *Dentex* spp.) in NW Africa from Casablanca to Cap Bojador | Stamatina Isari (IMR)
Theme 4 | Addressing population structure of shared demersal stocks | Arved Staby (IMR)
Theme 4 | Community structure and demersal habitats of the deeper shelf and upper slope of NWA | Arved Staby (IMR)
Theme 6 | Occurrence of marine debris in the regions surveyed by the RV *Dr Fridtjof Nansen* from 2011 and up to now. | Peter Kershaw (FAO consultant and GESAMP), BE Grøsvik (IMR)
Theme 6 | Further develop protocol on identification of marine debris (photos according to main categories agreed to) | Peter Kershaw (FAO consultant and GESAMP), BE Grøsvik (IMR)
Theme 7 | Characterization of benthic habitats based on epibenthos and infauna | Fran Ramil (University of Vigo)
Theme 9 | Current-driven upwelling in north west African upwelling system (agreed with Karim). - Workshop in Casablanca May-June); model work (Paul); supervision in Bergen April May Ismail Bessa (INRH) | Marek Ostrowski (IMR)
Theme 9 | Documenting the slow current along NW Africa | Marek Ostrowski (IMR)
Theme 9 | Habitat suitability | Marek Ostrowski (IMR)
Theme 10 | Paleoreconstruction of OMZ | Mohammed Idrissi (INRH)
Theme 10 | Monitoring pH and alcalinity | Melissa Chierici (IMR)
Theme 11 | Ecosystem characterization of the CCLME area | Cecilie Hansen (IMR)

## SO.taxonomy
FAMILY | CLASS
Squillidae - Mantis shrims | Crustacea
Aristeidae - Aristeid shrimps | Crustacea
Penaeidae - Penaeid shrimps | Crustacea
Palaemonidae - Palaemonid shrimps | Crustacea
Pandalidae - Pandalid shrimps | Crustacea
Nephropidae - True lobsters & langoustines | Crustacea
Palinuridae - Spiny lobsters | Crustacea
Scyllaridae - Slipper lobsters | Crustacea
Galatheidae Squat lobsters | Crustacea
Homolidae Paromolas | Crustacea
Calappidae - Box crabs | Crustacea
Majidae -Spider crabs | Crustacea
Geryonidae Deepsea crabs | Crustacea
Portunidae - Swimming crabs | Crustacea
Sepiidae - Cuttlefishes | Cephalopoda
Sepiolidae - Bobtail squids | Cephalopoda
Loliginidae - Inshore squids | Cephalopoda
Ommastephidae - Flying squids | Cephalopoda
Octopodidae - Benthic octopods | Cephalopoda

## SO.cruise.plan
Survey Name | Duration in days | Departure | Arrival | Port of Departure | Port of Arrival
Leg 2.1 Guinea-Mauritania | 32 | 26/02/2022 | 29/03/2022 | Las Palmas | Las Palmas
Leg 2.2 Cap Blanc-Casablanca | 32 | 04/02/2022 | 03/05/2022 | Las Palmas | Las Palmas

## SO.requested.participants
Leg | Position /laboratory | DFN core team | Morocco | Mauritania | Senegal | Gambia | Guinee | Guinea Bissau | External experts
Leg2.1 | Cruise leader | 1
Leg2.1 | Co-cruise leader |  |  | 1
Leg2.1 | Water chemistry | 1 |  | 1 | 1 | 1
Leg2.1 | Physical oceanography | 1 |  | 1 | 1
Leg2.1 | Plankton biology | 1 |  | 1 | 1
Leg2.1 | Fisheries biology / taxonomy | 2 |  | 1 | 1 | 1 | 1 | 1
Leg2.1 | Benthos |  |  | 1 |  |  | 1 | 1 | 2
Leg2.1 | Nutrition and fish safety
Leg2.1 | Whale / Seabird observatory
Leg2.1 | Local authority |  |  |  | 1
Leg2.2 | Cruise leader | 1
Leg2.2 | Co-cruise leader |  | 1
Leg2.2 | Water chemistry | 1 | 2 | 1
Leg2.2 | Physical oceanography | 1 |  | 1 | 1
Leg2.2 | Plankton biology | 1 | 2 | 1 |  | 1
Leg2.2 | Fisheries biology / taxonomy | 2 | 4 | 2 | 1
Leg2.2 | Benthos |  |  | 1 |  |  |  |  | 1
Leg2.2 | Nutrition and fish safety
Leg2.2 | Whale / Seabird observatory
Leg2.2 | Local authority

## SO.planned.participants
LEG | PARTICIPANT | ROLE | E-MAIL | SEX | AFFILIATION | COUNTRY
Leg 2.1 | Erik Olsen | Cruise leader | eriko@hi.no | M | IMR | NORWAY
Leg 2.1 | Jessica Hough | Fish Team Leader | jessyahough@hi.no | F | IMR | NORWAY
Leg 2.1 | Bernadine Everett | Fish Team Leader | bernadine.everett@hi.no | F | IMR | SOUTH AFRICA
Leg 2.1 | Sara Zamora Terol | Plankton Team Leader | sara.zamora.terol@hi.no | F | IMR | SPAIN
Leg 2.1 | Ba Mamadou Lamba | Chemical oceanography team leader | elkhalilmohamed98@gmail.com | M |  | MAURITANIA
Leg 2.1 | Kouame Kanga Desire | Physical oceanography team leader | kangadesirek@gmail.com> | M |  | CÔTE D'IVOIRE
Leg 2.1 | Olaf Sørås | Chief Instruments Engineer | olaf.j.soeraas@hi.no | M | IMR | NORWAY
Leg 2.1 | Jori Neteland Kyte | Instruments Engineer | jori.neteland-kyte@hi.no | F | IMR | NORWAY
Leg 2.1 | Raymond Koivogui | Benthos team | raymondkoivogui@gmail.com | M |  | GUINEA
Leg 2.1 | Noelo Silva Akys Cardoso | Benthos team | noelo.akys@gmail.com | M |  | GUINEA-BISSAU
Leg 2.1 | Jaime Moreno Aguillar | Fish team | JAIMEMA282@gmail.com | M |  | SPAIN
Leg 2.1 | Modou Lamin Conteh | Fish team | Modoulaminconteh0@gmail.com | M |  | GAMBIA
Leg 2.1 | Diafode Traore | Fish team | dtraore19@yahoo.fr | M |  | GUINEA
Leg 2.1 | Diosnes Manuel Nonque | Plankton team | diosnesss@hotmail.com | M |  | GUINEA-BISSAU
Leg 2.1 | Ahmed Diange | Fish team | diagne_ameth@yahoo.fr | M |  | MAURITANIA
Leg 2.1 | Ba Samba Assane | Fish team | basambaalassane@gmail.com | M |  | MAURITANIA
Leg 2.1 | Abdoulie B Jallow | Chemical oceanography team | abdouliebjallow@gmail.com | M |  | GAMBIA
Leg 2.1 | Mohamed Beyih Ould | Plankton team | mohamedbeyih@yahoo.fr | M |  | MAURITANIA
Leg 2.1 | Mohamed Mohamed Mahmoud | Chemical Oceanography teams | elkhalilmohamed98@gmail.com | M |  | MAURITANIA
Leg 2.1 | Simone Dacruz | Plankton team | simonalabelle@yahoo.fr | M |  | SENEGAL
Leg 2.1 | Marta Gil Gonzales | Benthos team | martag@uvigo.es | F |  | SPAIN
Leg 2.1 | Henar Antolinez Fernandez | Benthos team | henar.antolinez.fernandez@uvigo.es | F |  | SPAIN
Leg 2.1 | Ndague Diogoul | Physical oceanography team | diogoulndague@yahoo.fr | M |  | SENEGAL
Leg 2.1 | Peter Psomadakis | Fish team (taxonomist) | peter.psomadakis@fao.org | F |  | ITALY
Leg 2.1 | Houmeya Mohamed Yahya | Physical oceanography team | ouldhamiya@yahoo.fr | M |  | MAURITANIA
Leg 2.1 | NAVY OFFICER Senegal | Other |  | M |  | SENEGAL
LEG | PARTICIPANT | ROLE | E-MAIL | SEX | AFFILIATION | COUNTRY
Leg 2.2 | Jens-Otto Krakstad | Cruise leader |  | M | IMR | Norway
Leg 2.2 | Sarah Ann Bruck | Fish Team Leader |  | F | IMR | Norway
Leg 2.2 | Vidar Fauskanger | Fish Team Leader |  | M | IMR | Norway
Leg 2.2 | Jorunn Sanden | Plankton Team Leader |  | F | IMR | Norway
Leg 2.2 | David Cervantes | Chemical oceanography Team Leader |  | M | IMR | Norway
Leg 2.2 | Adil Chair | Physcical oceanographer Team Leader |  | M | INRH | Morocco
Leg 2.2 | Leif Johan Ohnstad | Chief Instruments Engineer |  | M | IMR | Norway
Leg 2.2 | Jan Frode Wilhelmsen | Instruments Engineer |  | M | IMR | Norway
Leg 2.2 | Ahmed El Achi | Co-Cruise leader |  | M | INRH | Morocco
Leg 2.2 | Djimera Lassana | Fish Team | DjimeraL2001@gmail.com | M | IMROP | Mauritania
Leg 2.2 | Deddache Saleck Moilick | Fish Team | salddache@yahoo.fr | M | IMROP | Mauritania
Leg 2.2 | BEGOÑA SOTILLO DE OLANO | Fish team /FAO taxonomist | begona.sotillo@ieo.es | F | IEO | Spain
Leg 2.2 | AbdelAziz Gharnati | Fish Team |  | M | INRH | Morocco
Leg 2.2 | Zakaria Zouine | Fish Team |  | M | INRH | Morocco
Leg 2.2 | Abdelkarim Kalmouni | Fish Team |  | M | INRH | Morocco
Leg 2.2 | N.N. Senegal | Fish Team
Leg 2.2 | Khalid Limam Malick | Chemical oceanography | limamahmado@gmail.com | M | IMROP | Mauritania
Leg 2.2 | Mohammed Idrissi | Chemical oceanography |  | M | INRH | Morocco
Leg 2.2 | Aziz Agouzouk | Chemical oceanography |  | M | INRH | Morocco
Leg 2.2 | Gandega cheikhna | Plankton Team | gandega_cheikhna@yahoo.fr | M | IMROP | Mauritania
Leg 2.2 | Tarek Baibai | Plankton Team |  | M | INRH | Morocco
Leg 2.2 | Yassine Gouilat (Doctorant) | Plankton Team |  | M | INRH | Morocco
Leg 2.2 | Sidi Mohamed | Benthos team |  | M | IMROP | Mauritania
Leg 2.2 | Belén Calero | Benthos team | bcalero@uvigo.es | F | UVigo | Spain
Leg 2.2 | Sara Castillo | Benthos team | scastillo@uvigo.es | F | UVigo | Spain
Leg 2.2 | Rezzoum Nouddrine | Benthos team |  | M | INRH | Morocco

## SO.additional.sampling
SAMPLE FOR GENETICS
STA N° | SAMPLE N° | BOX N° | N°INSIDE | FAMILY | SPECIES/TAXA | TL (mm) | SL (mm) | DW | ML | PHOTO
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .
. | . | . | . | . | . | . | . | . | . | .

## SO.equipmenttab
Component sampled | Equipment
Physical-air | Weather station (wind speed, direction, temperature, light sensor)
Physical-water | CTDO, Fluorescence sensor, PAR sensor; 150kHz ADCP; thermosalinograph (T,S,Fl); turbidity sensor
Chemical-water | Water samples and chemical analysis, pH, AT, pCO2, nutrient analyzer; fluorometer instrument, salinity, oxygen
Phytoplankton | Water samples (quantitative), Chlorophyll analysis from fluorometer instrument
Zooplankton | WP2 (180 µm), Bongo net (180 µm), Multinet midi (180 µm), Echo sounders (EK 80), flow cam,
Ichthyoplankton and jellyfish | Multinet midi (180 µm), Multinet mammoth (180 µm and 405 µm), Bongo net (180 µm), CUFES (continuous underwater fish egg sampler)
Fish (incl. mesopelagic fish) | Pelagic (Åkra trawl, MultPelt trawl) and Demersal trawls (Gisund Super), Echo sounders (EK 80), Omni-directional Fisheries sonar (SH 90)
Benthos | Demersal trawl (Gisund)
Plastic | Manta trawl (180 mµ), demersal and pelagic trawl
Mammals and seabirds
Bathymetry | Olex (with input from EM 710)

## SO.datahandovertab
Data types | Data | after the survey | at the post survey meeting | upon request | not collected/stored | analyzed by partner country | analyzed through the Science Plan
Acoustic data | EK80 narrowband (CW) |  |  | x
Acoustic data | EK80 broadband (FM) |  |  |  | x
Acoustic data | MS70 |  |  |  | x
Acoustic data | ME70 |  |  |  | x
Acoustic data | SU90 |  |  |  | x
Acoustic data | SH90 |  |  |  | x
Acoustic data | SBP300 |  |  |  | x
Acoustic data | EM302 |  | x
Acoustic data | EM710 |  | x
Physics | CTD probe | x
Physics | CTD Underway |  |  |  | x
Physics | ADCP 75kHz |  |  |  | x
Physics | ADCP 150kHz | x
Physics | LADCP |  |  |  | x
Physics | Thermosalinograph | x
Physics | Nutrients |  | x
Physics | pH | x
Physics | Total alkalinity | x
Physics | PCO2 | x
Physics | Chlorophyll | x
Biology | Trawl catch data | x | x
Biology | Zooplankton biomass |  | x
Biology | Phytoplankton |  |  |  | x
Pollution | Microplastics | [5 empty] | x
Observation platforms | VAMS |  |  |  | x
Observation platforms | WBAT |  |  |  | x
Observation platforms | Deep vision |  |  |  | x
Observation platforms | Scanmar |  |  | x
Observation platforms | Activity diary (cruise logger) | x
Observation platforms | Nansis survey backup |  |  | x

## SO.collectedsamplestab
Gear/equipment | Analysis | Samples | Preservation | Port of offloading | Type of transportation | Institution address | Contact details (name, email, phone no) | Deadline for analysis | Data and sampling types for future usage and reference
Rosette water bottles | Nutrients. Will be analysed on board after the survey | Water samples | Frozen (as requested by the partner country) | N/A | N/A | IMR - Nansen | "David Cervantes" <david.cervantes@hi.no> | 2022-02-01
WP2 (180 µm) from max 200 m 1/2 Split | Zooplankton biomass estimation | Aluminium trays | Dried and then frozen | Las Palmas | Sea freight | IMR, Bergen | Stamatina Isari
WP2 (180 µm) from max 200 m 1/2 Split | Zooplankton community identification | Bottles with ½ of bulk WP2 sample | 4% formaldehyde | Las Palmas | Sea freight | INRH, Casablanca | Omar Ettahiri
Bongo H (405 µm) Leg 2.1 | Ichthyoplankton community identification, genetics | Bottles with bulk sample | 96% ethanol | Las Palmas | Sea freight | INRH, Casablanca | Omar Ettahiri
Bongo V (405 µm) Leg 2.1 | Ichthyoplankton community identification | Bottles with bulk sample | 4% formaldehyde | Las Palmas | Sea freight | FSSD Ghana | Hawa Bint Yaqub
Bongo V(405 µm) Leg 2.1 | Species identification | Scintillation vials with sorted larval fish from the bulk bongo sample | 4% formaldehyde | Las Palmas | Sea freight | FSSD Ghana | Hawa Bint Yaqub
Bongo H (405 µm) Leg 2.2 | Ichthyoplankton community identification, genetics | Bottles with bulk sample | 96% ethanol | Las Palmas | Sea freight | INRH, Casablanca | Omar Ettahiri
Bongo V (405 µm) Leg 2.2 | Ichthyoplankton community identification | Bottles with bulk sample | 4% formaldehyde | Las Palmas | Sea freight | INRH, Casablanca | Omar Ettahiri
Bongo V(405 µm) Leg 2.2 | Species identification | Scintillation vials with sorted larval fish from the bulk bongo sample | 4% formaldehyde | Las Palmas | Sea freight | INRH, Casablanca | Omar Ettahiri
Gear/equipment | Analysis | Samples | Preservation | Port of offloading | Type of transportation | Institution address | Contact person Leg 3.1 (e-mail, phone no) | Deadline for analysis
Manta trawl (335 µm): surface tow for 15 mins | Neuston community identification | Bottles with bulk sample | 96% ethanol | Las Palmas | Sea freight | INRH, Casablanca | Omar Ettahiri
| Species identification, Genetics | Scintillation vials with sorted larval fish and eggs from the bulk manta sample | 96% ethanol | Las Palmas | Sea freight | INRH, Casablanca | Omar Ettahiri
| Abundance and chemical composition of microplastics | Eppendorf tubes with the microplastics sorted from the bulk manta sample | Photographed, stored in Eppendorf tubes at room temperature | Las Palmas | Sea freight | IMR | Bjørn Einar Grøsvik
Trawl samples | Whole Merluccius sp for determinaiton of maturity, otoliths, parasites, genetics and morphometrics | Whole fish | Frozen | Las Palmas | Sea freight | ? | ?
Trawl samples | Taxonomic identification – problematic species – Peter | Whole fish, cephalopods, invertebrates | Frozen (>20 cm length) or 10% Formalin | Las Palmas | Sea freight | Formaline: Off-loaded in LP
[6 empty] | Frozen: sent to IMR | / Peter Psomadakis/Sarah Bruck
Trawl samples | Taxonomic identification – Unidentified species | Whole fish | Frozen (>20 cm length) or 10% Formalin | Las Palmas | Road | FAO
|  |  | Genetic from ind. in formaline |  |  |  | / Peter Psomadakis/Sarah Bruck
Trawl samples | Taxonomic identification – Post survey training course | Whole fish, invertebrates | Frozen | Las Palmas |  | Frozen: sent to IMR | Peter Psomadakis / Sarah Bruck
Trawl samples | Taxonomic identification- IMR Training course | Whole fish | Frozen | Las Palmas | Sea freight | IMR | Sarah Bruck/Diana Zaera
Trawl samples | Genetics (stock identity) | Finclips of selected species (list of species) | 96% Ethanol | Las Palmas | Sea freight | IMR | Geir/Maria
Trawl samples | Nutrition and Food Safety | Whole fish | Frozen | Las Palmas | Sea freight | IMR | Mariann Kjellevold
Trawl samples | Taxonomy | Epibenthos | ? | Las palmas | ? | ? | ?
Grab samples | Taxonomy | Infauna | ? | Las palmas | ? | ? | ?

## SO.matstagetab
Stage | State | Description
I | Immature | Ovary and testis about 1/3rd length of body cavity. Ovaries pinkish, translucent, testis whitish. Ova not visible to naked eye.
II | Maturing virgin and recovering spent | Ovary and testis about ½ length of body cavity. Ovary pinkish, translucent, testis whitish, symmetrical. Ova not visible to naked eye.
III | Ripening | Ovary and testis is about 2/3rds length of body cavity. Ovary pinkish yellow colour with granular appearance, testis whitish to creamy. No transparent or translucent ova visible.
IV | Ripe | Ovary and testis from 2/3rds to full length of body cavity. Ovary orange-pink in colour with conspicuous superficial blood vessels. Large transparent, ripe ova visible. Testis whitish-creamy, soft.
V | Spent | Ovary and testis shrunken to about ½ length of body cavity. Walls loose. Ovary may contain remnants of disintegrating opaque and ripe Ova, darkened or translucent. Testis bloodshot and flabby

## SO.biosampling
Species | Catch (Weight / Numbers) | Length frequency | Sex/Maturity | Otoliths | Parasites | Genetics | Morphometrics
*Merluccius merluccius* | YES | YES | YES | **YES** | **YES** | **YES** | **YES**
*Merluccius polli* | YES | YES | YES | **YES** | **YES** | **YES** | **YES**
*M. senegalensis* | YES | YES | YES | **YES** | **YES** | **YES** | **YES**
*Pagellus bellottii* | YES | YES | YES | YES
*P.acarne* | YES | YES | YES | YES
*Dentex macrophthalmus* | YES | YES | YES | YES
*Parapeneaus longirostris* | YES | YES | SEX ONLY
*Aristeus varidens* | YES | YES | SEX ONLY
*Penaeopsis serrata * | YES | YES
*Trichiurus lepturus * | YES | YES
*Lepidopus caudatus * | YES | YES
*Todarodes sagittatus * | YES | YES
*Illex coindetii * | YES | YES
*Todaropsis eblanae * | YES | YES
*Ommastrephes bartramii * | YES | YES
*Thysanoteuthis rhombus * | YES | YES
*Brama brama * | YES | YES
*Helicolenus dactylopterus * | YES | YES
*Trachyscorpia cristulata * | YES | YES
*Octopus vulgaris* | YES | YES
All remaining species caught | YES